## RACI Matrix
# | Phase | Node ID | Step Description | Type | Tier | Gate Type | Conditional | Deliverable Section | Functional Category | Company Counsel | Issuer (Mgmt) | Underwriters | UW Counsel | Accountants | Reserve Engineer | Tax Counsel | SEC/FINRA/Exch
Phase 1: Strategic Decision & IPO Readiness
| Phase 1: Strategic Decision & IPO Readiness | Milestone_IPOTrigger | TRIGGER: Sponsor decides to pursue IPO | MILESTONE
1 | Phase 1: Strategic Decision & IPO Readiness | Issuer_EvalStrategicOptions | Issuer: Evaluate strategic options (IPO vs. alternatives; market timing) | ACTION | Human |  |  | Cross-section | Administrative |  | R
| Phase 1: Strategic Decision & IPO Readiness | Decision_ProceedIPO | Proceed with IPO? | DECISION |  | QC Checkpoint
2 | Phase 1: Strategic Decision & IPO Readiness | CompCounsel_DetermineFilerStatus | Company Counsel: Compile revenue, float & debt data; apply Securities Act thresholds; produce filer status memo | ACTION | LLM |  |  | Cross-section | Regulatory Filing | R | A
3 | Phase 1: Strategic Decision & IPO Readiness | CompCounsel_SelectAccommodations | Company Counsel: Map & select available EGC/SRC/JOBS Act/FAST Act accommodations | ACTION | LLM |  | Varies by filer status (EGC/SRC/neither) | Cross-section | Administrative | R | A
4 | Phase 1: Strategic Decision & IPO Readiness | Issuer_IPOReadiness | Issuer: Perform IPO readiness assessment | ACTION | Human |  |  | Cross-section | Administrative | I | R
5 | Phase 1: Strategic Decision & IPO Readiness | CompCounsel_ProduceStalenessCalendar | Company Counsel: Calculate staleness deadlines (Reg S-X Rule 3-12); produce calendar with update triggers | ACTION | LLM |  |  | Cross-section | Compliance Verification | R | A
6 | Phase 1: Strategic Decision & IPO Readiness | UW_SelectComparables | Underwriters: Search EDGAR for comparable MLP IPO filings; select based on market positioning | ACTION | Hybrid |  |  | Cross-section | Administrative | I |  | R
7 | Phase 1: Strategic Decision & IPO Readiness | Issuer_EstablishPMO | Issuer: Establish IPO PMO; align stakeholders | ACTION | Human |  |  | Cross-section | Administrative | I | R
Phase 2: Assembling the IPO Team
8 | Phase 2: Assembling the IPO Team | Issuer_SelectCompCounsel | Issuer: Select company counsel | ACTION | Human |  |  | Cross-section | Administrative | C | R
9 | Phase 2: Assembling the IPO Team | Issuer_SelectAuditor | Issuer: Select independent auditor (PCAOB-registered) | ACTION | Human |  |  | Cross-section | Administrative | C | R
10 | Phase 2: Assembling the IPO Team | Issuer_SelectLeadUW | Issuer: Select lead underwriter(s) & co-managers | ACTION | Human |  |  | Cross-section | Administrative | C | R
11 | Phase 2: Assembling the IPO Team | UW_SelectUWCounsel | Underwriters: Select underwriters' counsel | ACTION | Human |  |  | Cross-section | Administrative | I |  | R
12 | Phase 2: Assembling the IPO Team | Issuer_RetainResEng | Issuer: Retain reserve engineers | ACTION | Human |  |  | Cross-section | Administrative |  | R
13 | Phase 2: Assembling the IPO Team | Issuer_RetainTaxCounsel | Issuer: Retain tax counsel | ACTION | Human |  |  | Cross-section | Tax & Structure |  | R
14 | Phase 2: Assembling the IPO Team | Issuer_SelectPrinterTA | Issuer: Select financial printer & transfer agent | ACTION | Human |  |  | Cross-section | Administrative |  | R
Phase 3: MLP Structure & Formation
15 | Phase 3: MLP Structure & Formation | TaxCounsel_DetermineQI | Tax Counsel: Analyze qualifying income framework (§7704(d)(1)(E)); apply to revenue streams; issue determination | ACTION | Hybrid |  | MLP-specific; skip for corporate IPO | Cross-section | Tax & Structure | C | A |  |  |  |  | R
| Phase 3: MLP Structure & Formation | Decision_QualifyingIncome | Qualifying income test met? | DECISION |  | QC Checkpoint
16 | Phase 3: MLP Structure & Formation | Issuer_SelectDistModel | Issuer: Assess cash flow profile; select distribution model | ACTION | Human |  |  | Cross-section | Administrative |  | R
17 | Phase 3: MLP Structure & Formation | CompCounsel_DetermineConveyanceFeasibility | Company Counsel: Identify consent requirements & indenture restrictions; make feasibility determination | ACTION | Hybrid |  |  | Cross-section | Compliance Verification | R | A
18 | Phase 3: MLP Structure & Formation | CompCounsel_DraftLPCert | Company Counsel: Draft certificate of limited partnership (DE) | ACTION | LLM |  |  | Certificate of LP | Tax & Structure | R | A
19 | Phase 3: MLP Structure & Formation | CompCounsel_FileFormation | Company Counsel: Draft GP entity formation docs (LLC cert + OA); file with DE Secretary of State | ACTION | Hybrid |  |  | GP Formation Docs | Regulatory Filing | R | A
20 | Phase 3: MLP Structure & Formation | CompCounsel_DraftCapTermSheet | Company Counsel: Draft capitalization term sheet (IDR, subordination, MQD) | ACTION | Hybrid |  |  | Cap Term Sheet | Tax & Structure | R | A
21 | Phase 3: MLP Structure & Formation | CompCounsel_NegotiateCapTerms | Company Counsel: Negotiate & finalize economic terms; produce revised term sheet reflecting agreed terms | ACTION | Human |  |  | Cross-section | Tax & Structure | R | A
22 | Phase 3: MLP Structure & Formation | Issuer_EstablishGPGov | Issuer: Establish GP governance; appoint independent directors | ACTION | Human |  |  | Cross-section | Administrative | C | R
23 | Phase 3: MLP Structure & Formation | CompCounsel_DraftLPA | Company Counsel: Draft LPA from precedent & term sheet; make governance & fiduciary duty decisions; produce circulation draft (Ex 3.2) | ACTION | Hybrid |  |  | Exhibit 3.2: LPA | Tax & Structure | R | A |  |  |  |  | C
24 | Phase 3: MLP Structure & Formation | CompCounsel_DraftContribAgreement | Company Counsel: Draft Contribution Agreement; adapt reps, indemnification & closing conditions | ACTION | Hybrid |  |  | Contribution Agreement | Disclosure Drafting | R | A
25 | Phase 3: MLP Structure & Formation | CompCounsel_DraftRegRights | Company Counsel: Draft Registration Rights Agreement; adapt demand/piggyback rights & shelf terms | ACTION | Hybrid |  |  | Registration Rights Agreement | Disclosure Drafting | R | A
26 | Phase 3: MLP Structure & Formation | CompCounsel_DraftMSA | Company Counsel: Draft Services Agreement (MSA); negotiate scope, fees & termination provisions | ACTION | Hybrid |  |  | Services Agreement | Disclosure Drafting | R | A
27 | Phase 3: MLP Structure & Formation | CompCounsel_DraftLTIP | Company Counsel: Draft LTIP plan document; determine award types, vesting & share reserve | ACTION | Hybrid |  |  | LTIP Plan Document | Disclosure Drafting | R | A
28 | Phase 3: MLP Structure & Formation | CompCounsel_DraftAncillary | Company Counsel: Draft ancillary agreements (Omnibus, Tax Receivable, etc.); adapt to deal terms; incorporate revisions | ACTION | Hybrid |  |  | Ancillary Agreements | Disclosure Drafting | R | A
Phase 4: Organizational Meeting & Due Diligence
29 | Phase 4: Organizational Meeting & Due Diligence | Issuer_HoldOrgMeeting | Issuer: Hold organizational / all-hands meeting | ACTION | Human |  |  | Cross-section | Administrative |  | R
30 | Phase 4: Organizational Meeting & Due Diligence | CompCounsel_CirculateChecklist | Company Counsel: Compile & circulate responsibility checklist & DD request list to working group | ACTION | LLM |  |  | Cross-section | Administrative | R | A
31 | Phase 4: Organizational Meeting & Due Diligence | CompCounsel_DistributeQuestionnaire | Company Counsel: Customize & distribute D&O questionnaires to officers, directors & nominees | ACTION | LLM |  |  | Cross-section | Administrative | R | A
32 | Phase 4: Organizational Meeting & Due Diligence | CompCounsel_DraftLockUp | Company Counsel: Draft lock-up agreement; determine period, exceptions & early release provisions | ACTION | Hybrid |  |  | Lock-Up Agreement | Disclosure Drafting | R | A
33 | Phase 4: Organizational Meeting & Due Diligence | CompCounsel_DraftCommsPlan | Company Counsel: Draft quiet period / gun-jumping compliance policy; tailor to company circumstances | ACTION | Hybrid |  |  | Communications Policy | Compliance Verification | R | A
34 | Phase 4: Organizational Meeting & Due Diligence | UWCounsel_ConductBizLegalDD | UW Counsel: Conduct business & legal due diligence | ACTION | Human |  |  | Cross-section | Due Diligence | C |  | A | R
35 | Phase 4: Organizational Meeting & Due Diligence | Acct_ConductFinDD | Accountants: Conduct financial due diligence | ACTION | External |  |  | Cross-section | Due Diligence | I | A |  |  | R
36 | Phase 4: Organizational Meeting & Due Diligence | Acct_ConfirmComfortReadiness | Accountants: Confirm auditor readiness for comfort letters | ACTION | External |  |  | Cross-section | Compliance Verification | I | A |  |  | R
37 | Phase 4: Organizational Meeting & Due Diligence | ResEng_CommissionReserves | Reserve Engineer: Commission reserve reports (S-K 1200/1202) | ACTION | External |  |  | Cross-section | Due Diligence | I | A |  |  | I | R
| Phase 4: Organizational Meeting & Due Diligence | Decision_DDAcceptable | DD findings acceptable? | DECISION |  | QC Checkpoint
Phase 5: Corporate & Governance Matters
38 | Phase 5: Corporate & Governance Matters | CompCounsel_DraftReorgPlan | Company Counsel: Draft reorganization step plan; determine entity structure, tax elections & jurisdictions | ACTION | Hybrid |  |  | Reorganization Plan | Tax & Structure | R | A |  |  |  |  | C
39 | Phase 5: Corporate & Governance Matters | CompCounsel_DraftGovGuidelines | Company Counsel: Draft governance guidelines & code of ethics | ACTION | LLM |  |  | Governance Guidelines | Disclosure Drafting | R | A
40 | Phase 5: Corporate & Governance Matters | CompCounsel_DraftInsiderPolicy | Company Counsel: Draft & tailor insider trading policy per Rule 10b5-1 to entity structure & board prefs | ACTION | Hybrid |  |  | Insider Trading Policy | Compliance Verification | R | A
41 | Phase 5: Corporate & Governance Matters | CompCounsel_DraftLTIPAdoption | Company Counsel: Draft plan adoption resolutions; finalize plan terms & board approval documentation | ACTION | Hybrid |  |  | LTIP Plan Document | Disclosure Drafting | R | A
42 | Phase 5: Corporate & Governance Matters | CompCounsel_DraftIndemnification | Company Counsel: Draft indemnification agreement; adapt scope & limitations to entity & state law | ACTION | Hybrid |  |  | Indemnification Agreement | Disclosure Drafting | R | A
43 | Phase 5: Corporate & Governance Matters | Issuer_ObtainDOInsurance | Issuer: Obtain D&O insurance | ACTION | Human |  |  | Cross-section | Administrative | I | R
44 | Phase 5: Corporate & Governance Matters | Issuer_BoardResolutions | Issuer: Board/GP board resolutions authorizing IPO | ACTION | Human |  |  | Cross-section | Administrative | C | R | I
| Phase 5: Corporate & Governance Matters | Decision_BoardAuthorizes | Board authorizes IPO? | DECISION |  | QC Checkpoint
45 | Phase 5: Corporate & Governance Matters | CompCounsel_DraftPOA | Company Counsel: Draft POA forms; compile executed POAs for Exhibit 24.1 | ACTION | LLM |  |  | Exhibit 24.1: POA | Exhibit Assembly | R | A
46 | Phase 5: Corporate & Governance Matters | CompCounsel_DraftConsents | Company Counsel: Draft consent forms; compile executed consents for Exhibits 99.5–99.7 | ACTION | LLM |  |  | Exhibits 99.5-99.7: Consents | Exhibit Assembly | R | A
Phase 6: Financial Statement Preparation
47 | Phase 6: Financial Statement Preparation | Acct_DetermineRegistrantFS | Accountants: Determine appropriate registrant FS (predecessor/carve-out) | ACTION | External |  |  | Cross-section | Financial Production | I | A |  |  | R
48 | Phase 6: Financial Statement Preparation | Acct_PrepareAuditedFS | Accountants: Prepare audited annual FS per PCAOB / Reg S-X | ACTION | External |  |  | Cross-section | Financial Production | I | A |  |  | R
49 | Phase 6: Financial Statement Preparation | Acct_PrepareInterimFS | Accountants: Prepare unaudited interim FS | ACTION | External |  | Required if >134 days from FYE at effectiveness | Cross-section | Financial Production | I | A |  |  | R
50 | Phase 6: Financial Statement Preparation | Acct_DetermineProFormaAdj | Accountants: Structure pro forma template & draft assumptions (Art. 11); determine adjustments & validate | ACTION | External |  | Skip if no reorganization transactions | Cross-section | Financial Production | I | A |  |  | R
51 | Phase 6: Financial Statement Preparation | Acct_DetermineNonGAAPMeasures | Accountants: Draft reconciliation tables & Reg G format; determine non-GAAP measures to present & validate | ACTION | External |  |  | Cross-section | Financial Production | I | A |  |  | R
52 | Phase 6: Financial Statement Preparation | Issuer_PrepareDCFForecast | Issuer: Prepare four-quarter DCF forecast (MLP-specific) | ACTION | Human |  | MLP-specific; skip for corporate IPO | Cross-section | Financial Production |  | R
53 | Phase 6: Financial Statement Preparation | Acct_DetermineDCFAdjustments | Accountants: Structure DCF backcast template; make substantive judgments on pro forma adjustments | ACTION | External |  | MLP-specific; skip for corporate IPO | Cross-section | Financial Production | I | A |  |  | R
54 | Phase 6: Financial Statement Preparation | ResEng_PrepareReserveData | Reserve Engineer: Prepare reserve report data & reconciliation | ACTION | External |  |  | Cross-section | Financial Production | I | A |  |  | I | R
55 | Phase 6: Financial Statement Preparation | CompCounsel_DraftMarketRisk | Company Counsel: Draft S-K Item 305 disclosure; integrate hedging data; make materiality determinations | ACTION | Hybrid |  |  | Item 7A: Market Risk | Disclosure Drafting | R | A |  |  | C | C
56 | Phase 6: Financial Statement Preparation | Acct_XBRLTagging | Accountants: XBRL tagging of FS (Reg S-T; specialized software) | ACTION | External |  |  | Cross-section | Financial Production | I | A |  |  | R
57 | Phase 6: Financial Statement Preparation | Acct_MonitorStaleness | Accountants: Monitor & manage FS staleness; update as needed | ACTION | External |  |  | Cross-section | Compliance Verification | I | A |  |  | R
58 | Phase 6: Financial Statement Preparation | Acct_ResolvePredecessor | Accountants: Resolve predecessor accounting determination (ASC 805) | ACTION | External |  | Skip if no predecessor entity | Cross-section | Financial Production | I | A |  |  | R
| Phase 6: Financial Statement Preparation | Decision_VDRReady | All inputs ready for S-1 drafting? | DECISION |  | QC Checkpoint
Phase 7: S-1 Drafting & Content Preparation
59 | Phase 7: S-1 Drafting & Content Preparation | CompCounsel_InitiateS1Drafting | Company Counsel: Kick off parallel S-1 section drafting across all tracks | ACTION | Human |  |  | Cross-section | Disclosure Drafting | R | A
60 | Phase 7: S-1 Drafting & Content Preparation | CompCounsel_DraftFrontMatter | Company Counsel: Assemble cover page & draft disclaimers (Industry/Market Data, Trademarks, BoP) | ACTION | LLM |  |  | Cover Page & Disclaimers | Disclosure Drafting | R | A
61 | Phase 7: S-1 Drafting & Content Preparation | CompCounsel_DraftRiskFactors | Company Counsel: Draft risk factors; organize categories; make materiality judgments; cross-reference (Item 1A) | ACTION | Hybrid |  |  | Item 1A: Risk Factors | Disclosure Drafting | R | A,C
62 | Phase 7: S-1 Drafting & Content Preparation | CompCounsel_DraftUseOfProceeds | Company Counsel: Draft Use of Proceeds; determine allocation disclosure & specific use language | ACTION | Hybrid |  |  | Item 3: Use of Proceeds | Disclosure Drafting | R | A,C
63 | Phase 7: S-1 Drafting & Content Preparation | CompCounsel_DraftDistPolicy | Company Counsel: Draft Cash Distribution Policy from LPA terms; determine subordination mechanics; produce waterfall table & sensitivity analysis | ACTION | Hybrid |  | MLP-specific; skip for corporate IPO | Cash Distribution Policy | Disclosure Drafting | R | A,C |  |  |  |  | C
64 | Phase 7: S-1 Drafting & Content Preparation | CompCounsel_DraftCapTable | Company Counsel: Assemble capitalization table from agreed financial data | ACTION | LLM |  |  | Item 5: Capitalization | Financial Production | R | A |  |  | C
65 | Phase 7: S-1 Drafting & Content Preparation | CompCounsel_DraftDilution | Company Counsel: Compute dilution analysis from pricing assumptions | ACTION | LLM |  | Skip if no dilution to public investors | Item 6: Dilution | Disclosure Drafting | R | A |  |  | C
66 | Phase 7: S-1 Drafting & Content Preparation | CompCounsel_DraftHistFinData | Company Counsel: Compile financial data into standardized table format; draft narrative wrapper | ACTION | LLM |  | 2yr if EGC; 5yr otherwise | Selected Financial Data | Financial Production | R | A |  |  | C
67 | Phase 7: S-1 Drafting & Content Preparation | CompCounsel_DraftMDA | Company Counsel: Structure MD&A; draft period-over-period analysis; incorporate management input & forward-looking statements | ACTION | Hybrid |  |  | Item 7: MD&A | Disclosure Drafting | R | A,C |  |  | C
68 | Phase 7: S-1 Drafting & Content Preparation | CompCounsel_DraftBusiness | Company Counsel: Draft Business section from VDR data, reserve reports & public sources; ensure S-K 1200/1202 compliance | ACTION | Hybrid |  |  | Item 1: Business | Disclosure Drafting | R | A,C |  |  | C | C
69 | Phase 7: S-1 Drafting & Content Preparation | CompCounsel_DraftMgmt | Company Counsel: Draft Management section from D&O questionnaires; make disclosure adequacy & related-party judgments | ACTION | Hybrid |  |  | Item 10: Management | Disclosure Drafting | R | A,C
70 | Phase 7: S-1 Drafting & Content Preparation | CompCounsel_DraftComp | Company Counsel: Draft CD&A narrative & compensation tables; determine peer group, metrics & EGC scaled disclosure (S-K Item 402) | ACTION | Hybrid |  | Scaled disclosure if EGC | Item 11: Compensation | Disclosure Drafting | R | A,C
71 | Phase 7: S-1 Drafting & Content Preparation | CompCounsel_DraftOwnershipTable | Company Counsel: Compile ownership data & produce table per S-K Item 403 | ACTION | LLM |  |  | Item 12: Ownership | Disclosure Drafting | R | A
72 | Phase 7: S-1 Drafting & Content Preparation | CompCounsel_DraftRelatedTxn | Company Counsel: Draft Related Transactions; make materiality judgments on transactions to disclose | ACTION | Hybrid |  |  | Item 13: Related Transactions | Disclosure Drafting | R | A,C
73 | Phase 7: S-1 Drafting & Content Preparation | CompCounsel_DraftUnitDesc | Company Counsel: Draft Description of Common Units from LPA terms; verify accuracy of material rights | ACTION | Hybrid |  |  | Description of Common Units | Disclosure Drafting | R | A |  |  |  |  | C
74 | Phase 7: S-1 Drafting & Content Preparation | CompCounsel_DraftConflicts | Company Counsel: Draft Conflicts of Interest from LPA fiduciary provisions; cross-reference against UnitDesc & LPA terms | ACTION | Hybrid |  | MLP-specific; skip for corporate IPO | Conflicts of Interest | Disclosure Drafting | R | A |  |  |  |  | C
75 | Phase 7: S-1 Drafting & Content Preparation | CompCounsel_DraftFLS | Company Counsel: Draft PSLRA safe harbor disclaimer; tailor cautionary language to company-specific statements | ACTION | Hybrid |  |  | Forward-Looking Statements | Disclosure Drafting | R | A
76 | Phase 7: S-1 Drafting & Content Preparation | CompCounsel_DraftPartII | Company Counsel: Draft Part II (Items 13–15: expenses, indemnification, exhibits & FS schedules) | ACTION | LLM |  |  | Part II (Items 13-15) | Disclosure Drafting | R | A
77 | Phase 7: S-1 Drafting & Content Preparation | CompCounsel_CompileExhibitIndex | Company Counsel: Compile exhibit index cross-referenced to S-K Item 601 | ACTION | LLM |  |  | Exhibit Index | Exhibit Assembly | R | A
78 | Phase 7: S-1 Drafting & Content Preparation | CompCounsel_DraftUndertakings | Company Counsel: Draft undertakings (S-K Item 512); cross-reference exhibit index against actual exhibits | ACTION | LLM |  |  | Item 17: Undertakings | Disclosure Drafting | R | A
79 | Phase 7: S-1 Drafting & Content Preparation | CompCounsel_AssembleExhibits | Company Counsel: Assemble all exhibits with correct numbering & EDGAR refs; verify completeness; manage consent logistics; produce final package | ACTION | Hybrid |  |  | Exhibits | Exhibit Assembly | R | A
80 | Phase 7: S-1 Drafting & Content Preparation | CompCounsel_DraftBackMatter | Company Counsel: Compile LPA appendix & generate glossary of defined terms | ACTION | LLM |  |  | Appendix & Glossary | Exhibit Assembly | R | A
81 | Phase 7: S-1 Drafting & Content Preparation | CompCounsel_AssembleSigPages | Company Counsel: Assemble signature pages with officer/director names & titles; attach POA references | ACTION | LLM |  |  | Signature Pages (Ex 24.1) | Exhibit Assembly | R | A
82 | Phase 7: S-1 Drafting & Content Preparation | CompCounsel_DraftSummary | Company Counsel: Draft Prospectus Summary from business description & deal terms; determine emphasis, positioning & materiality (drafted last / most revised) | ACTION | Hybrid |  |  | Prospectus Summary | Disclosure Drafting | R | A,C | I
83 | Phase 7: S-1 Drafting & Content Preparation | TaxCounsel_DraftTax | Tax Counsel: Draft MLP tax section; determine specific tax positions & qualifying income conclusions; incorporate into disclosure | ACTION | Hybrid |  |  | Tax Considerations | Disclosure Drafting | C | A |  |  |  |  | R
84 | Phase 7: S-1 Drafting & Content Preparation | UWCounsel_DraftUW | UW Counsel: Draft Underwriting section from precedent & deal terms; adapt stabilization, over-allotment & syndicate provisions | ACTION | Hybrid |  |  | Underwriting | Disclosure Drafting |  |  | A | R
| Phase 7: S-1 Drafting & Content Preparation | Decision_SectionsConsistent | Internal cross-reference QC passed? | DECISION |  | QC Checkpoint
Phase 8: Initial Filing
85 | Phase 8: Initial Filing | CompCounsel_FileFormID | Company Counsel: File Form ID with SEC for EDGAR access codes | ACTION | LLM |  |  | Cross-section | Regulatory Filing | R | A | [5 empty] | I
86 | Phase 8: Initial Filing | CompCounsel_AssembleDRS | Company Counsel: Assemble complete DRS with sections, exhibits & EDGAR headers; verify completeness; authorize submission | ACTION | Hybrid |  |  | Cross-section | Exhibit Assembly | R | A | I | C |  |  |  | I
| Phase 8: Initial Filing | Milestone_DRSFiled | FILED: DRS confidentially submitted | MILESTONE
87 | Phase 8: Initial Filing | CompCounsel_CoordinatePostDRS | Company Counsel: Coordinate parallel post-DRS filings (FINRA + exchange) | ACTION | Human |  |  | Cross-section | Administrative | R | A
88 | Phase 8: Initial Filing | UWCounsel_CompileFINRA | UW Counsel: Compile FINRA Rule 5110 information; draft application; verify compensation; authorize filing | ACTION | Hybrid |  |  | Cross-section | Exhibit Assembly | C |  | A | R
89 | Phase 8: Initial Filing | Issuer_FileListingApp | Issuer: File listing application with stock exchange | ACTION | Human |  |  | Cross-section | Regulatory Filing |  | R | I
90 | Phase 8: Initial Filing | CompCounsel_AssembleDRSA | Company Counsel: Assemble DRS/A incorporating all revisions; verify; authorize submission | ACTION | Hybrid |  |  | Cross-section | Exhibit Assembly | R | A | I | C |  |  |  | I
91 | Phase 8: Initial Filing | CompCounsel_AssembleS1 | Company Counsel: Assemble complete S-1 with all sections & exhibits; authorize public 'flip'; coordinate EDGAR | ACTION | Hybrid |  |  | Cross-section | Exhibit Assembly | R | A | I | C |  |  |  | I
| Phase 8: Initial Filing | Milestone_S1Public | FILED: S-1 publicly filed | MILESTONE
92 | Phase 8: Initial Filing | CompCounsel_DraftForm8A | Company Counsel: Draft & format Form 8-A for EDGAR submission | ACTION | LLM |  |  | Form 8-A | Regulatory Filing | R | A
Phase 9: SEC Review Cycle
93 | Phase 9: SEC Review Cycle | SEC_ReviewRS | SEC/FINRA/Exchange: SEC reviews registration statement (~30 days) | ACTION | External |  |  | Cross-section | Review & QC | I |  | I | I |  |  |  | R
| Phase 9: SEC Review Cycle | Decision_SECComments | SEC issues comments? | DECISION |  | External Gate
94 | Phase 9: SEC Review Cycle | CompCounsel_DistributeComments | Company Counsel: Parse comment letter; categorize, assess significance & develop response strategy; distribute analyzed comments with assignments | ACTION | Hybrid |  |  | Cross-section | Review & QC | R | A
95 | Phase 9: SEC Review Cycle | CompCounsel_DraftCORRESP | Company Counsel: Draft proposed responses & redline prospectus language; exercise judgment on strategy; produce formatted CORRESP letter | ACTION | Hybrid |  |  | CORRESP Letter | Review & QC | R | A |  | C
96 | Phase 9: SEC Review Cycle | CompCounsel_AssembleS1A | Company Counsel: Integrate approved changes into amended S-1; verify completeness; authorize S-1/A filing | ACTION | Hybrid |  |  | Cross-section | Exhibit Assembly | R | A | I | C |  |  |  | I
97 | Phase 9: SEC Review Cycle | CompCounsel_CompileConsents | Company Counsel: Generate updated consent forms; compile executed consents as exhibits for filing | ACTION | LLM |  |  | Exhibits 99.5-99.7: Consents | Exhibit Assembly | R | A
98 | Phase 9: SEC Review Cycle | CompCounsel_RefileOpinions | Company Counsel: Re-file opinions (legality, tax) with each amendment | ACTION | Hybrid |  |  | Exhibits 5.1/8.1: Opinions | Regulatory Filing | R | A
99 | Phase 9: SEC Review Cycle | Acct_UpdateFSDuringReview | Accountants: Update FS if required during review period | ACTION | External |  |  | Cross-section | Financial Production | I | A |  |  | R
| Phase 9: SEC Review Cycle | Decision_SECFurtherComments | SEC has further comments? | DECISION |  | External Gate
100 | Phase 9: SEC Review Cycle | CompCounsel_DraftSubsequent | Company Counsel: Draft responses to subsequent round comments; finalize & coordinate amendment | ACTION | Hybrid |  |  | CORRESP Letter | Review & QC | R | A |  | C
101 | Phase 9: SEC Review Cycle | CompCounsel_ConfirmClearance | Company Counsel: Confirm SEC clearance & coordinate next steps | ACTION | Human |  |  | Cross-section | Compliance Verification | R | A | I
| Phase 9: SEC Review Cycle | Milestone_SECClear | CLEAR: SEC clears — no further comments | MILESTONE
102 | Phase 9: SEC Review Cycle | CompCounsel_PopulatePricing | Company Counsel: Populate all pricing blanks throughout S-1; verify accuracy of populated fields | ACTION | LLM |  |  | Cross-section | Disclosure Drafting | R | A | C
103 | Phase 9: SEC Review Cycle | CompCounsel_VerifyTiming | Company Counsel: Verify timing compliance (15-calendar-day rule); assemble filing; authorize public filing | ACTION | Hybrid |  |  | Cross-section | Compliance Verification | R | A
Phase 10: FINRA Review
104 | Phase 10: FINRA Review | SEC_FINRAReview | SEC/FINRA/Exchange: FINRA reviews underwriting compensation | ACTION | External |  |  | Cross-section | Review & QC | I |  | I | I |  |  |  | R
| Phase 10: FINRA Review | Decision_FINRAClears | FINRA clears? | DECISION |  | External Gate
105 | Phase 10: FINRA Review | UWCounsel_ResolveFINRA | UW Counsel: Draft responses to FINRA compensation comments; negotiate resolution | ACTION | Hybrid |  |  | Cross-section | Review & QC | C |  | A | R
Phase 11: Pre-Effectiveness & Marketing
106 | Phase 11: Pre-Effectiveness & Marketing | CompCounsel_PrintProspectus | Company Counsel: Print & distribute preliminary prospectus (red herring) | ACTION | Human |  |  | Cross-section | Regulatory Filing | R | A | I
107 | Phase 11: Pre-Effectiveness & Marketing | Issuer_ConductRoadshow | Issuer: Conduct roadshow (management presentations; 1–2 weeks) | ACTION | Human |  |  | Cross-section | Administrative |  | R | I
108 | Phase 11: Pre-Effectiveness & Marketing | UW_BuildOrderBook | Underwriters: Form syndicate; build order book | ACTION | Human |  |  | Cross-section | Administrative | I |  | R | C
| Phase 11: Pre-Effectiveness & Marketing | Decision_SufficientDemand | Sufficient investor demand at price range? | DECISION |  | QC Checkpoint
| Phase 11: Pre-Effectiveness & Marketing | Decision_RepriceOrAbandon | Reprice or abandon? | DECISION |  | QC Checkpoint
109 | Phase 11: Pre-Effectiveness & Marketing | CompCounsel_DraftAccelRequest | Company Counsel: Draft & format Rule 461 acceleration request for EDGAR submission | ACTION | LLM |  |  | Acceleration Request | Regulatory Filing | R | A | C
110 | Phase 11: Pre-Effectiveness & Marketing | CompCounsel_ProduceFeeTable | Company Counsel: Compute filing fees (SEC Rule 457); produce Exhibit 107 filing fee table | ACTION | LLM |  |  | Exhibit 107: Fee Table | Financial Production | R | A | C
| Phase 11: Pre-Effectiveness & Marketing | Decision_AccelerationGranted | SEC grants acceleration? | DECISION |  | External Gate
Phase 12: Effectiveness
111 | Phase 12: Effectiveness | SEC_DeclaresEffective | SEC/FINRA/Exchange: SEC declares registration statement effective | ACTION | External |  |  | Cross-section | Regulatory Filing | I |  | I | I |  |  |  | R
| Phase 12: Effectiveness | Milestone_Effective | SEC DECLARES REGISTRATION STATEMENT EFFECTIVE — END — | MILESTONE
Kill Path
| Kill Path | Milestone_IPOAbandoned | IPO ABANDONED — END | MILESTONE

## Legend
1. RACI Definitions
R — Responsible | Performs the work. Exactly one R per action step.
A — Accountable | Approves or owns the outcome. The party with legal or contractual liability.
C — Consulted | Provides input before or during the work. Two-way communication.
I — Informed | Notified after completion. One-way communication.
2. Role Color Key
Company Counsel | Okabe-Ito #0072B2
Issuer (Management) | Okabe-Ito #E69F00
Underwriters | Okabe-Ito #56B4E9
UW Counsel | Okabe-Ito #009E73
Accountants | Okabe-Ito #F0E442
Reserve Engineer | Okabe-Ito #D55E00
Tax Counsel | Okabe-Ito #CC79A7
SEC/FINRA/Exchange | Okabe-Ito #000000
3. Interpretive Notes
Note 1 | Decision and milestone nodes have no RACI assignments (process control points).
Note 2 | Issuer (Management) is Accountable for most steps as the registrant with Section 11 liability.
Note 3 | Underwriters are Accountable for UW Counsel steps as the engaging party.
Note 4 | SEC/FINRA/Exchange steps have no separate Accountable — external regulatory actions.
Note 5 | Where a role is both R and A, only R is shown.
Note 6 | Where Issuer is both A and C (e.g., management provides substantive input to CC drafting and approves the outcome), the cell shows 'A,C'.
4. Precedent Transaction Reference
Entity | Mach Natural Resources LP
CIK | 0001980088
Filing type | S-1 Registration Statement
Filing dates | S-1 filed 2023-09-22; 3 S-1/A amendments (2023-09-29, 2023-10-05, 2023-10-16); effective 2023-10-24 (32 days from initial S-1)
Amendments | 3 S-1/A amendments, 2 CORRESP letters; no DRS/DRS-A
EDGAR URL | https://www.sec.gov/cgi-bin/browse-edgar?action=getcompany&CIK=0001980088
5. Entity & Deliverable Definitions
MLP | A Master Limited Partnership (MLP) is a publicly traded partnership — not a corporation — that typically owns midstream oil & gas infrastructure. MLPs are pass-through entities for tax purposes; investors receive K-1s, not 1099s. The GP manages the partnership; limited partners hold publicly traded units.
S-1 Registration | An S-1 registration statement is the SEC filing required to register securities for an initial public offering. It contains a prospectus (narrative disclosure, financial statements, risk factors, management information) and exhibits (legal opinions, material contracts, consents). The SEC reviews the filing and issues comments; the company amends until cleared.
6. Key Terms Glossary
DRS | Draft Registration Statement — confidential SEC submission
DRS/A | Amendment to the confidential DRS
S-1/A | Public amendment to the S-1 registration statement
CORRESP | Correspondence letter responding to SEC comments
Reg S-K | SEC regulation governing non-financial disclosure requirements
Reg S-X | SEC regulation governing financial statement requirements
PCAOB | Public Company Accounting Oversight Board — auditing standards
EDGAR | SEC's Electronic Data Gathering, Analysis, and Retrieval system
Red Herring | Preliminary prospectus distributed during roadshow (no final price)
Gun-Jumping | Prohibited offers/publicity before or during the registration period
Comfort Letter | Auditor's letter confirming FS accuracy for underwriters' due diligence
VDR | Virtual Data Room — secure repository of deal documents for due diligence
IDR | Incentive Distribution Right — GP economic entitlement above MQD thresholds
MQD | Minimum Quarterly Distribution — base LP distribution before IDR tiers
Rule 5110 | FINRA rule requiring disclosure and review of underwriting compensation
7. Tier Classification Methodology
Basis | Classification reflects whether a frontier LLM (Claude Opus 4.6 or equivalent successor within 6 months) can produce the work product — not whether a human reviews it afterward.
LLM | LLM can produce filing-quality output given inputs; senior reviewer accepts with only minor, non-substantive edits.
Hybrid | LLM produces substantial first draft (60-80%); human must make material substantive decisions about content, framing, or completeness.
Human | Requires 100% human judgment, negotiation, physical action, or access to undisclosed information.
External | Performed by outside party (SEC, auditors, reserve engineers) whose work product the team receives but does not produce.
Data dependency | Steps requiring proprietary third-party data as inputs but where the LLM can perform the production work are Hybrid, not Human. Steps that merely receive and file third-party output are External.
Reference | Full tier definitions: Mermaid Flowchart Instruction Manual vT15, Section 2.3
8. Source Material Citations
S1: Latham & Watkins | US IPO Guide (2025); Global IPO Guide; US Financial Statements Guide; Annex A Checklist
S2: Deloitte + Skadden | Strategies for Going Public (5th Ed.)
S3: PwC | Roadmap for an IPO
S4: Vinson & Elkins | MLP Primer Brochure (2018)
S5: EY | Guide to Going Public; Strategic Considerations Before, During and Post-IPO
Precedent filings | Mach Natural Resources LP SEC filings (DRS, DRS/A, S-1, S-1/A ×3, CORRESP ×2, EFFECT)
Regulatory | Securities Act of 1933; Reg S-K; Reg S-X; FINRA Rule 5110; IRC §7704; ASC 805; PCAOB Standards
9. Team Roster & Attribution
Ezequiel Padilla | VDR Captain / Methodology Author: defined scope, validated role assignments, approved tier classifications, directed all structural decisions.
Claude Opus 4.6 | LLM Co-Producer: drafted Mermaid code, proposed tier classifications, built RACI matrix, produced analytical sheets.

## Summary
Role | R Count | A Count | C Count | I Count
Company Counsel | 68 | 0 | 10 | 23
Issuer (Mgmt) | 17 | 84 | 9 | 0
Underwriters | 3 | 4 | 3 | 13
UW Counsel | 4 | 0 | 7 | 3
Accountants | 12 | 0 | 6 | 2
Reserve Engineer | 2 | 0 | 2 | 0
Tax Counsel | 2 | 0 | 5 | 0
SEC/FINRA/Exch | 3 | 0 | 0 | 5
TOTAL | 111 | 88 | 42 | 46
Tier | Count | Pct
LLM | 25 | 22.52%
Hybrid | 44 | 39.64%
Human | 25 | 22.52%
External | 17 | 15.32%

## Chapter-Level Tier Matrix
Deliverable Section | LLM | Hybrid | Human | External | Total | Dominant Tier
Acceleration Request | 1 | 0 | 0 | 0 | 1 | LLM
Ancillary Agreements | 0 | 1 | 0 | 0 | 1 | Hybrid
Appendix & Glossary | 1 | 0 | 0 | 0 | 1 | LLM
CORRESP Letter | 0 | 2 | 0 | 0 | 2 | Hybrid
Cap Term Sheet | 0 | 1 | 0 | 0 | 1 | Hybrid
Cash Distribution Policy | 0 | 1 | 0 | 0 | 1 | Hybrid
Certificate of LP | 1 | 0 | 0 | 0 | 1 | LLM
Communications Policy | 0 | 1 | 0 | 0 | 1 | Hybrid
Conflicts of Interest | 0 | 1 | 0 | 0 | 1 | Hybrid
Contribution Agreement | 0 | 1 | 0 | 0 | 1 | Hybrid
Cover Page & Disclaimers | 1 | 0 | 0 | 0 | 1 | LLM
Cross-section | 7 | 11 | 25 | 17 | 60 | Human
Description of Common Units | 0 | 1 | 0 | 0 | 1 | Hybrid
Exhibit 107: Fee Table | 1 | 0 | 0 | 0 | 1 | LLM
Exhibit 24.1: POA | 1 | 0 | 0 | 0 | 1 | LLM
Exhibit 3.2: LPA | 0 | 1 | 0 | 0 | 1 | Hybrid
Exhibit Index | 1 | 0 | 0 | 0 | 1 | LLM
Exhibits | 0 | 1 | 0 | 0 | 1 | Hybrid
Exhibits 5.1/8.1: Opinions | 0 | 1 | 0 | 0 | 1 | Hybrid
Exhibits 99.5-99.7: Consents | 2 | 0 | 0 | 0 | 2 | LLM
Form 8-A | 1 | 0 | 0 | 0 | 1 | LLM
Forward-Looking Statements | 0 | 1 | 0 | 0 | 1 | Hybrid
GP Formation Docs | 0 | 1 | 0 | 0 | 1 | Hybrid
Governance Guidelines | 1 | 0 | 0 | 0 | 1 | LLM
Indemnification Agreement | 0 | 1 | 0 | 0 | 1 | Hybrid
Insider Trading Policy | 0 | 1 | 0 | 0 | 1 | Hybrid
Item 10: Management | 0 | 1 | 0 | 0 | 1 | Hybrid
Item 11: Compensation | 0 | 1 | 0 | 0 | 1 | Hybrid
Item 12: Ownership | 1 | 0 | 0 | 0 | 1 | LLM
Item 13: Related Transactions | 0 | 1 | 0 | 0 | 1 | Hybrid
Item 17: Undertakings | 1 | 0 | 0 | 0 | 1 | LLM
Item 1: Business | 0 | 1 | 0 | 0 | 1 | Hybrid
Item 1A: Risk Factors | 0 | 1 | 0 | 0 | 1 | Hybrid
Item 3: Use of Proceeds | 0 | 1 | 0 | 0 | 1 | Hybrid
Item 5: Capitalization | 1 | 0 | 0 | 0 | 1 | LLM
Item 6: Dilution | 1 | 0 | 0 | 0 | 1 | LLM
Item 7: MD&A | 0 | 1 | 0 | 0 | 1 | Hybrid
Item 7A: Market Risk | 0 | 1 | 0 | 0 | 1 | Hybrid
LTIP Plan Document | 0 | 2 | 0 | 0 | 2 | Hybrid
Lock-Up Agreement | 0 | 1 | 0 | 0 | 1 | Hybrid
Part II (Items 13-15) | 1 | 0 | 0 | 0 | 1 | LLM
Prospectus Summary | 0 | 1 | 0 | 0 | 1 | Hybrid
Registration Rights Agreement | 0 | 1 | 0 | 0 | 1 | Hybrid
Reorganization Plan | 0 | 1 | 0 | 0 | 1 | Hybrid
Selected Financial Data | 1 | 0 | 0 | 0 | 1 | LLM
Services Agreement | 0 | 1 | 0 | 0 | 1 | Hybrid
Signature Pages (Ex 24.1) | 1 | 0 | 0 | 0 | 1 | LLM
Tax Considerations | 0 | 1 | 0 | 0 | 1 | Hybrid
Underwriting | 0 | 1 | 0 | 0 | 1 | Hybrid

## Per-Phase Tier Breakdown
Phase | LLM | Hybrid | Human | External | Total | LLM+Hybrid %
Phase 1: Strategic Decision & IPO Readiness | 3 | 1 | 3 | 0 | 7 | 57.14%
Phase 2: Assembling the IPO Team | 0 | 0 | 7 | 0 | 7 | 0%
Phase 3: MLP Structure & Formation | 1 | 10 | 3 | 0 | 14 | 78.57%
Phase 4: Organizational Meeting & Due Diligence | 2 | 2 | 2 | 3 | 9 | 44.44%
Phase 5: Corporate & Governance Matters | 3 | 4 | 2 | 0 | 9 | 77.78%
Phase 6: Financial Statement Preparation | 0 | 1 | 1 | 10 | 12 | 8.333%
Phase 7: S-1 Drafting & Content Preparation | 10 | 15 | 1 | 0 | 26 | 96.15%
Phase 8: Initial Filing | 2 | 4 | 2 | 0 | 8 | 75%
Phase 9: SEC Review Cycle | 2 | 6 | 1 | 2 | 11 | 72.73%
Phase 10: FINRA Review | 0 | 1 | 0 | 1 | 2 | 50%
Phase 11: Pre-Effectiveness & Marketing | 2 | 0 | 3 | 0 | 5 | 40%
Phase 12: Effectiveness | 0 | 0 | 0 | 1 | 1 | 0%

## Per-Phase Inputs & Outputs
Phase | Key Documents Ingested | Key Outputs Produced
Phase 1: Strategic Decision & IPO Readiness | Market data; prior-period financials; Securities Act threshold data; comparable EDGAR filings | Filer status memo; EGC/SRC accommodation map; staleness calendar; comparables list; IPO readiness assessment
Phase 2: Assembling the IPO Team | Filer status memo; IPO readiness assessment; market comparables | Engagement letters for all advisors (counsel, auditors, UW, reserve engineers, tax counsel, printer/TA)
Phase 3: MLP Structure & Formation | Tax code (IRC §7704); revenue stream data; precedent LPAs; organizational charts | QI determination; LP Certificate; GP formation docs; LPA draft (Ex 3.2); capitalization term sheet; 5 transaction agreements
Phase 4: Organizational Meeting & Due Diligence | DD request list; D&O questionnaires; material contracts; title documents; financial records; reserve data | Responsibility checklist; completed questionnaires; lock-up agreements; communications policy; DD reports; comfort letter readiness confirmation; reserve reports
Phase 5: Corporate & Governance Matters | Entity structure; board composition; compensation data; insurance quotes | Reorganization plan; governance guidelines; insider trading policy; LTIP adoption resolutions; indemnification agreements; D&O insurance binder; board resolutions; POAs; consents
Phase 6: Financial Statement Preparation | General ledger; trial balances; predecessor entity data; reserve reports; hedging data | Audited annual FS; interim FS; pro forma adjustments; non-GAAP reconciliations; DCF forecast; DCF adjustments; reserve data reconciliation; market risk disclosure; XBRL-tagged FS
Phase 7: S-1 Drafting & Content Preparation | VDR contents; all Phase 1-6 outputs; management input; D&O questionnaires; LPA; reserve reports | Complete S-1 prospectus (all sections); tax disclosure; underwriting section; cross-referenced and QC-verified draft
Phase 8: Initial Filing | Complete S-1 draft; EDGAR access codes; FINRA Rule 5110 data; exchange listing application | Form ID filed; DRS submitted; FINRA application filed; listing application filed; DRS/A submitted; S-1 publicly filed; Form 8-A filed
Phase 9: SEC Review Cycle | SEC comment letters; precedent CORRESP responses; updated FS; pricing data | CORRESP letters; S-1/A amendments; updated consents; re-filed opinions; pricing amendment; SEC clearance
Phase 10: FINRA Review | FINRA compensation comments; Rule 5110 filing | FINRA response letters; FINRA no-objections clearance
Phase 11: Pre-Effectiveness & Marketing | Preliminary prospectus; investor target list; order book data; pricing range | Red herring distributed; roadshow completed; order book; acceleration request (Rule 461); fee table (Exhibit 107)
Phase 12: Effectiveness | SEC acceleration request; FINRA clearance; fee table | SEC effectiveness order; registration statement declared effective

## Team Allocation Matrix
Role | LLM | Hybrid | Human | External | Total
Company Counsel | 25 | 38 | 5 | 0 | 68
Issuer (Mgmt) | 0 | 0 | 17 | 0 | 17
Underwriters | 0 | 1 | 2 | 0 | 3
UW Counsel | 0 | 3 | 1 | 0 | 4
Accountants | 0 | 0 | 0 | 12 | 12
Reserve Engineer | 0 | 0 | 0 | 2 | 2
Tax Counsel | 0 | 2 | 0 | 0 | 2
SEC/FINRA/Exch | 0 | 0 | 0 | 3 | 3
TOTAL | 25 | 44 | 25 | 17 | 111